## Project Setup
Field | Value (fill this column) | Hint
Programme ID (short, no spaces) |  | e.g. UST_FEWOFF25, RFQ_BLINQ, BEZEL_VW_SK216 Ã¢â‚¬â€ must be unique
Programme Name |  | Human-readable. Shows on dashboards.
Customer / Sponsor |  | External (UST, Vazirani) or "DContour Internal"
Strategic Intent (the WHY) |  | Why does this project exist? Win Stellantis / capability growth / etc.
Intent Kind | CAPABILITY | CUSTOMER_DEAL / PRODUCT_ROADMAP / TECH_ROADMAP / CAPABILITY / PARTNERSHIP
Archetype | CAPABILITY_GROWTH | (set by template Ã¢â‚¬â€ do not change)
Template ID | BLANK | (set by template Ã¢â‚¬â€ do not change)
Kickoff Date (YYYY-MM-DD) |  | When does Wk 1 start?
SOP Target / End Date (YYYY-MM-DD) |  | For mini-projects, just an end date
Programme Weeks | 40 | Suggested for this archetype: 40
Programme Owner (you) |  | Your name
Markets (comma-separated) |  | EU, IN, USA Ã¢â‚¬â€ leave blank for internal
Scope Parts (comma-separated) |  | SFH, RL, BEZEL, HDLP Ã¢â‚¬â€ what physical parts
Total Kits / Units |  | For Tier-1: 53 etc. For mini/recurring: blank.
Notes |  | Anything else worth knowing

## WBS
WBS | Level | Name | Phase | Discipline | Part | Start Wk | Finish Wk | Effort hr | Resources | Predecessor | Deliverable | Evidence Required | DGL / Checklist Ref
1.0 | 1 | INFRASTRUCTURE & EQUIPMENT |  | MFG | ALL
2.0 | 1 | PROCESS DEFINITION |  | MFG | ALL
3.0 | 1 | TRAINING & CERTIFICATION |  | PM | ALL
4.0 | 1 | FIRST ARTICLE VALIDATION |  | T-Q | ALL
1.1.1 | 3 | Equipment specification + PO |  | MFG | ALL | 1 | 8 | 32
2.1.1 | 3 | SOP + control plan |  | MFG | ALL | 12 | 20 | 40
3.1.1 | 3 | Team training plan |  | PM | ALL | 16 | 24 | 24
4.1.1 | 3 | First article report |  | T-Q | ALL | 28 | 36 | 32

## DPDS Gates
Gate | Deliverable | Kind | Required? | Status / Notes
Ã¢â‚¬â€ DPDS gate deliverables will be auto-populated when the programme is created from this template (based on archetype: Capability Growth). You can edit them post-creation.

## Team
Resource Code | Role | Person Name | Allocation % | Notes
Mfg-L1 |  |  | 100
T-L1 |  |  | 100
PM-1 |  |  | 100

## Milestones
Week | Event | Type | Phase | Owner | Notes

## Evidence Vault
WBS | Task | Evidence Kind | File / Vault Location | Acceptance Criteria | Owner | Status

## Instructions
Step | Instructions
1 | Archetype: Capability Growth
2 | Why this template: Build-train-certify. New equipment install, in-house process bring-up, training cohorts. PVD / extrusion / NexusCAD enablement.
3 | Ã¢â‚¬â€ HOW THIS EXCEL WORKS Ã¢â‚¬â€
4 | Each sheet (WBS, Team, Milestones, Evidence Vault) is an Excel TABLE. Click in the last row, press TAB at the end, and a new row is added automatically. No macros needed.
5 | Cells with dropdown arrows (Phase, Discipline, Part, Status, Evidence Kind, etc.) restrict to valid values Ã¢â‚¬â€ pick from the list to keep things clean for import.
6 | Ã¢â‚¬â€ FILL ORDER Ã¢â‚¬â€
7 | Step 1: "Project Setup" sheet Ã¢â‚¬â€ fill the YELLOW cells: Programme ID, Name, Customer, Strategic Intent (the WHY), Kickoff Date.
8 | Step 2: "WBS" sheet Ã¢â‚¬â€ sample tasks pre-filled. Adjust effort/weeks/resources. Add new rows by Tab. For each task, fill "Evidence Required" (what proves it is done) and "DGL / Checklist Ref" (which design guideline drives parameter tracking).
9 | Step 3: "Team" sheet Ã¢â‚¬â€ replace placeholder resource codes with real people and allocation %.
10 | Step 4: "Milestones" sheet Ã¢â‚¬â€ add gate reviews, customer reviews, sample deliveries.
11 | Step 5: "Evidence Vault" sheet Ã¢â‚¬â€ for each WBS task with deliverables, list the evidence kind (CAD file, sim report, test report, customer sign-off), where the file lives (vault path / link), and the acceptance criteria. This becomes the closure check.
12 | Step 6 (Tier-1 / R&D / Partnership only): DPDS gate deliverables auto-populate on import based on archetype Ã¢â‚¬â€ no need to fill them in this Excel.
13 | Ã¢â‚¬â€ TRIGGER Ã¢â‚¬â€
14 | Save the file. Open the platform Ã¢â€ â€™ Templates Ã¢â€ â€™ "Trigger Project from Excel" Ã¢â€ â€™ upload. Validation will preview and report any issues. Once accepted, the programme is created with WBS, milestones, team, evidence vault, and DPDS gates ready.
15 | Ã¢â‚¬â€ ONBOARDING TIP FOR FRESHERS Ã¢â‚¬â€
16 | Start with a MICRO_PROJECT template. No DPDS, just 4 sample tasks. Learn the rhythm: scope Ã¢â€ â€™ do Ã¢â€ â€™ review Ã¢â€ â€™ close. Then graduate to managing real customer programmes.
17 | Ã¢â‚¬â€ RECURRING PROJECTS Ã¢â‚¬â€
18 | Instead of WBS depth, you set Cadence (weekly / bi-weekly / monthly / quarterly) and target hours per instance in the Project Setup sheet. The platform will track expected vs actual hours per period.
19 | Ã¢â‚¬â€ EVIDENCE-VAULT FRAMEWORK (preview) Ã¢â‚¬â€
20 | Every task closure should be backtrackable: which CAD file proved the geometry, which sim report proved the photometry, which DGL was followed. This Excel captures the plan; the platform stores the actual files (data vault) and links them to the task.